- Appendix 1 Field Plan and Risk Assessment

A Field plan and risk assessment must be prepared prior to all fieldwork, except onshore in Denmark. For fieldwork onshore in Denmark, a field plan and risk assessment can be prepared; this decision is taken by the Project Manager and the responsible Head of Department.

The field plan shall provide an overview of the basic information related to the planned fieldwork, and at the same time help the Project Manager to get an overview of whether the participants chosen to take part in fieldwork, constitute an optimal team to complete the required tasks.

The purpose of the risk assessment is to identify potential risks in order to evaluate whether precautions need to be taken to minimise the identified risks.

By default, the Project Manager is also the acting Safety Officer and must inform of and involve all relevant persons in field planning and risk assessment. However, the Project Manager may appoint a colleague as expedition leader, cruise leader or field leader, who will then assume the responsibility of Safety Officer for that specific part of the project and it is this leader who will ensure that all field participants have received all necessary information. For each field plan, the Project Manager, possibly in collaboration with the Head of Department, must decide whether there is a need for an independent review of the field plan and risk assessment by a ‘safety consultant’. The safety consultant can be an external consultant but can also be an experienced colleague.

Field Plan and Risk Assessment for <Project xxx>

1	Field Plan – General Description of the Project

1.1	Basic Information

| Project | <official name, abbreviation, alias> |  |
| --- | --- | --- |
| Project Manager |  |  |
| Expedition/cruise leader | <name of appointed expedition, cruise or field leader> |  |
| Department |  |  |
| Telephone number |  |  |
| E-mail |  |  |
| Partners | <institution, contact person, e-mail, phone no.> |  |
| GEUS fieldwork | Yes ☐ | No ☐ |
|  | If no: <who is responsible for the health status of the participants, SAR, safety, insurance and permits to perform the work?> |  |
| Location | <Denmark, Greenland, other> |  |

Purpose of the Fieldwork:

<a short description of the purpose, time frame, etc. for the entire project>

Map of the Field Area/Expected Locations:

<insert a map of the fieldwork/project area, from Google Maps or GIS. Please mark the nearest hospital, medical clinic, police, airport, and other relevant information. If the area is very remote, an additional map at a larger scale to show these facilities should also be inserted.>

1.2	Plan for the Fieldwork

| What? | <short description of the actual fieldwork, that is planned in connection with the project, use of equipment, if any> |
| --- | --- |
| Start date | <from leaving home> |
| End date | <to return to home> |
| Transportation | <planned international or local transport, if any> |
| Safety Manager* | <is it necessary to appoint a Safety Manager? A Safety Manager is appointed if there are ten or more participants> |
| Radio time** | <what kind of contact to GEUS or others is agreed?> <which types of communication equipment is available?> |

*Unless otherwise agreed, the Project Manager is also the Safety Manager

**Radio time means communication with e.g. GEUS, but also internal communication between different field teams, this in order to be able to give a status on the participants’ well-being

1.3	Information About the Field Participants

| Name | Institution | Role/function | Comment |
| --- | --- | --- | --- |
| <Ole Olsen> | <GEUS> | <Glaciologist> |  |
| <Hanne Hansen> | <DTU> | <Geophysicist> |  |

2	Risk Assessment

2.1	Identification of Risks during the Planned Fieldwork

Risk assessments are a tool to create awareness and minimise the risk of injury or damage to persons, equipment, the environment and GEUS’ reputation.

Risk can be defined as the consequence x probability associated with an unwanted event. The purpose of the risk assessment is to evaluate whether an identified risk is acceptable or whether it can be minimised or eliminated by taking suitable precautions.

The risk assessment must be done well in advance of the planned fieldwork, so any precautions can be implemented without delays to the schedule. Please be aware that this is a desktop tool; with the purpose of increasing awareness to any risks that should be considered during the planning stage. The reality in the field can be very different from what was imagined at home, and it should always be observed conditions that determine decisions taken in the field.

Course of Action

- Table 3 can help to identify potential risks in relation to the fieldwork. Remember: Not everything is a risk, if you consider them carefully, e.g. it is obvious that you need enough food, water, fuel etc. when camping in the Arctic.

- For each identified risk, assess the probability (S1-S5) of the incident occurring (Table 1) and the severity of the consequences (C1-C5) if it occurs (Table 2).

- Calculate the risk level by multiplying the probability with the consequence (Table 4).

- In Table 6, list all the identified risks that you have found to be a potential risk in connection with the fieldwork

- Use Table 5 to decide whether precautions are needed to change the ‘probability’ and mitigate the severity of the ‘consequences’ if the incident occurs.

Table 1   Classes of probability S1 to S5.

| Probability | Category | Probability | Description |
| --- | --- | --- | --- |
|  | S5 | Very likely | Expected to happen several times during the fieldwork |
|  | S4 | Somewhat likely | Will happen sometimes during fieldwork |
|  | S3 | Possible | Has been registered for similar types of fieldwork, might happen once during the fieldwork |
|  | S2 | Rare | Have heard of similar incidents, but it is very unlikely that it will happen during fieldwork |
|  | S1 | Unlikely | Have never heard of a similar incident, will most likely not happen during fieldwork |

Table 2   Classes of consequence C1 to C5.

| Consequence | Category | Consequence | Description |
| --- | --- | --- | --- |
|  | C1 | Negligible | First aid injury |
|  | C2 | Minor | Medical treatment |
|  | C3 | Moderate | Absence injury, hospital stay |
|  | C4 | Major | Partially/permanently incapacitated |
|  | C5 | Catastrophic | Fatal accident |

Table 3   The list below can help to identify potential risks in relation to fieldwork.

| ✓ | Health Issues |
| --- | --- |
|  | Valid health certificate(s) |
|  | Appropriate clothing and personal equipment |
|  | Food and drinks (preferences / allergies) |
|  | Next of kin |
|  | Medication (allergies etc.) |
|  | Rabies |
|  | Parasites and possible infection or disease |
|  | Sanitation, hygiene, and risk of contagion |
|  | Workload/overtime – physical and mental exhaustion |
|  | Other things? |
| ✓ | Insurance |
|  | Travel insurance, is everyone covered? |
|  | Insurance of field equipment and personal equipment |
|  | Search & Rescue (SAR), is everyone covered? |
| ✓ | Safety Issues in General |
|  | The field parties’ route |
|  | Weather forecast for the period |
|  | How to handle bad weather conditions |
|  | Travelling over / movement on sea ice |
|  | Travelling over / movement on glaciers |
|  | Travelling / movement in difficult terrain |
|  | Travelling/moving in areas exposed to avalanches |
|  | Dangerous animals – equipment / agreements |
|  | Routines regarding firearms and pyrotechnics |
|  | Emergency procedures (radio medical, list of contacts) |
|  | Travelling / movement on melted Tundra |
|  | Crossing rivers |
|  | Means of communication |
|  | Communication routines |
|  | Distribution of safety equipment in the field party |
|  | Working on large vessels |
| ✓ | Use of Drones (UAV, UUV / AUS) |
|  | Permits in place? |
|  | Competence and certificates for pilots |
|  | Risk analysis |
| ✓ | Transportation by |
|  | Snow scooter. Organisation and driving procedures |
|  | Small boats. Safety instructions / mandatory safety briefing |
|  | Large vessels. Mandatory safety briefing |
|  | Large vessels – handling of equipment, navigation, weather, rescue equipment |
|  | Helicopter. Mandatory safety briefing. |
|  | Fixed winged airplane |
|  | Dog sledge |
|  | ATV |
|  | Car |
|  | On foot / ski |
|  | Information / announcing of field activities |
|  | Activities that might create public concern, or be of danger to the public |
| ✓ | Environmental Issues |
|  | Disturbance of wildlife special to the area and time period. |
|  | Waste disposal |
|  | Protected areas |
|  | Cultural heritage |
|  | Location of camp sites |
|  | Flora |
|  | Need for special permits / applications? |
| ✓ | Field Camp |
|  | Tents |
|  | Small cabins |
|  | Fire protection |
|  | CO2 poisoning |
|  | Polar bear protection |
|  | Location of the field camp, safety issues. |
|  | Communications from the field camp |
|  | Garbage / waste, routines, and handling |
|  | Access to clean water |
|  | Familiarity with use of camp equipment such as camp stoves, polar bear fence, etc. |
| ✓ | Organisation, Planning and Responsibilities |
|  | Leadership and responsibilities |
|  | When to report back to GEUS/base camp |
|  | Report when leaving/returning to a destination or field camp |
|  | Location of emergency equipment |
|  | Termination of fieldwork – when is it unsafe to continue the fieldwork? |
| ✓ | Mandatory Check-In/De-brief/Evaluation |
|  | Register incidents, accidents, or deviations |
|  | Restore / cleaning equipment after fieldwork |
|  | Need of debriefing / evaluation |
|  | Register polar bear sightings / incidents |
| ✓ | Special Operations |
|  | Handling heavy equipment |
|  | Handling heavy or dangerous machinery |
|  | Use of winch or similar |
|  | Handling chemicals |
|  | Use of toxic material |
|  | Need for special safety analyses / HSE analyses? |

Precautions. The need for precautions depends on the risk (Table 4). Table 5 shows when action is needed. If the risk is ‘extreme’ (red), it must, in principle, be assessed as unacceptable and the desired fieldwork cannot be carried out. If it is possible to reduce the ‘high’ risk (orange) in Table 5 by taking precautions, the fieldwork can probably be carried out.

Precautions can include extra training, consultation of safety experts, change in schedule, change in staffing, purchase/use of extra safety equipment, implementation of risk zones and much more. The specific precautions are chosen based on the actual situation.

Table 4   Risk matrix for risk assessment.

| Incident during fieldwork |  | Consequence (severity) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Negligible K1 | Minor K2 | Moderate K3 | Major K4 | Catastrophic K5 |
| Probability | Very likely S5 | Moderate 5 | High 10 | Extreme 15 | Extreme 20 | Extreme 25 |
|  | Likely S4 | Moderate 4 | High 8 | High 12 | Extreme 16 | Extreme 20 |
|  | Possible S3 | Low 3 | Moderate 6 | High 9 | High 12 | Extreme 15 |
|  | Rare S2 | Low 2 | Moderate 4 | Moderate 6 | High 8 | High 10 |
|  | Unlikely S1 | Low 1 | Low 2 | Low 3 | Moderate 4 | Moderate 5 |

Table 5   Risk matrix and need for precautions.

| Colour | Risk | Actions |
| --- | --- | --- |
|  | Extreme | If fieldwork must be carried out, precautions must be taken so the risk changes to orange |
|  | High | Detailed planning and preparedness are required |
|  | Moderate | Continuous assessment of possible/necessary precautions |
|  | Low | No immediate need for action. Precautions may prevent low risk from getting higher |

Table 6   Risks and possible precautions to mitigate consequences. Please remove the examples before completing the form.

| Order of priority | Risk description | Probability (1-5) | Consequence (1-5) | Overall rating (red, orange, yellow, green). Red, orange and yellow risks must be considered, green can be included. | Current precautions | Additional precautions | Is the risk considered to be a basic condition where precautions will only to a small extent influence the risk? (yes/no) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Risk of falling into crevasses when working on glaciers | 3 | 5 |  | Always work at least two persons together, walk with ropes between you and wear crampons. | Never go out alone or far away from your tent after dark (but you can go out to pee). | Yes |
| 2 | Risk of falling and spraining your foot while doing geological mapping | 2 | 3 |  | Work at least two persons together, so you can help the injured person. Arctic First Aid is a prerequisite. Always carry your satellite phone and PLB. |  | Yes |
| 3 | The duration of the field period is extended, and you run out of food | 2 | 2 |  | Bring food for two days more than planned. | Bring food for another two days. | No |
| 4 |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |
| … |  |  |  |  |  |  |  |

Prioritise, describe, and note identified risks. Note probability, consequence and colour. Describe current precautions and additional precautions, if any. Decide whether the risk is considered a basic condition for the fieldwork. Text and colours in lines 1-3 are examples; please delete these.

| Prepared by: | Date: |
| --- | --- |
| Updated by: | Date: |

2.2.1	Other Procedures for Risk Reduction/Elimination

Other procedures that may reduce or eliminate risks:

- Project-specific safety procedures

- Detailed planning of the fieldwork, including daily plans

- Agreements on regular communication between the field participants

- No work after dark

- Availability of emergency flares (if brought along)

- Communication equipment

- Recording of all events

- Not to proceed if in doubt.

- Clear agreements on what safety equipment is brought; see Table 7.

Table 7   List of safety equipment that should be considered when planning the fieldwork. The list is not exhaustive.

|  | Equipment |  | Number | Remarks |
| --- | --- | --- | --- | --- |
|  | Personal first aid kit |  |  |  |
|  | Medical box |  |  |  |
|  | Rifle, cal. .30-06 |  |  |  |
|  | Ammunition cal. .30-06 |  |  |  |
|  | Revolver, cal. .44 magnum |  |  |  |
|  | Ammunition cal. .44 magnum |  |  |  |
|  | Signal pistol |  |  |  |
|  | Red signal ammunition |  |  |  |
|  | Green signal ammunition |  |  |  |
|  | Brown signal ammunition (blitz / knald) |  |  |  |
|  | Signal pen (flares) |  |  |  |
|  | Communication equipment | Satellite telephone |  |  |
|  |  | Emergency beacon (PLB) |  |  |
|  |  | Garmin InReach |  |  |
|  |  | Cell phone |  |  |
|  |  | VHF radio |  |  |
|  | Spare batteries |  |  |  |
|  | Battery charger for VHF radio |  |  |  |
|  | Tripwire alarm |  |  |  |
|  | GEUS reco bag |  |  |  |
|  | Heliograph |  |  |  |
|  | Whistle |  |  |  |
|  | Safety goggles / shoes (boots) |  |  |  |
|  | Safety helmets (hardhats) |  |  |  |
|  | Avalanche search beacon |  |  |  |
|  | Glacier rescue kit |  |  |  |
|  | Life jackets, survival, and flotation suit |  |  |  |
|  | Map |  |  |  |
|  | Compass |  |  |  |
|  | GPS |  |  |  |
|  | Tools for minor repairs of e.g. rubber boats, snowmobiles etc. |  |  |  |
|  | Windproof bag (or bothy bag) |  |  |  |
|  | Extra fuel, oil, and other consumables |  |  |  |
|  | Helmet, safety shoes or safety boots, hearing protection, reflective vest and safety climbing harness. |  |  |  |

| The field plan is approved, and the risk assessment has been presented to the Head of Department on | Head of department |
| --- | --- |
| <dd-mm-yyyy> | <name and signature> |